## Summary
Easy Books — School Management System | QA Audit & Fix Report
Prepared | 2026-07-17 — ahead of first client demo
Scope | Full audit of School Management vertical: frontend, backend, database. Forms, validation, payroll, transactions/ledger, banking, payments, invoicing/QR, BS/AD calendar, attendance, and role-based access.
Bugs found | 26
Fixed tonight | 17
Logged as known issues (not blocking, documented) | 9
How to use this workbook
Bugs tab | Every issue found, whether fixed tonight or logged as a known follow-up. Status column says Fixed / Unfixed. Severity is color-coded.
Role-Service Matrix tab | Every backend API endpoint in the school module, which staff roles can call it, and a plain-English description. Parent/Student portal endpoints are listed separately since they use a different login system.
Important context
No prior bug-tracking Excel was found | The workspace, Desktop, Downloads, and Documents folders were searched — no existing "bugs" workbook was found on this machine to add a tab to. This is a new workbook. If one exists elsewhere, its bug history was not available to merge in.

## Bugs
# | Area | Severity | Issue | Impact | Location | Status | Notes / Next step
1 | Calendar / BS-AD | Critical | BS↔AD date converter's calendar table only covered BS 2000–2015 (~AD 1943–1959) | adToBs() silently returned "" and bsToAd() crashed for every current date. Corrupted fee receipt numbering, ledger dateBs on every posting, dashboard "this month" range, and could crash payroll runs. | shared/src/utils/nepali-date.ts | Fixed | Replaced hand-rolled table with the maintained nepali-date-converter library (BS 2000–2090). Same fix applied to the separate frontend copy in frontend/src/lib/nepaliDate.js so both sides agree.
2 | Payroll | Critical | Payroll page called REST routes that don't exist on the backend | List/Generate/Mark-Paid/Hold all returned 404 — payroll was completely non-functional from the browser despite the underlying payroll engine being correct. | frontend/src/pages/Payroll.jsx, backend/.../payroll.controller.ts | Fixed | Rewired frontend to the real payroll.engine endpoints (summary/process/calculate/mark-paid/hold). Added a new adjust endpoint so "Other Deductions" (an existing but unreachable schema field) can actually be edited.
3 | Staff Attendance | Critical | Marking staff attendance always failed (400 Bad Request) | Frontend sent lowercase status values ('present') and check_in/check_out field names; backend requires uppercase enum (PRESENT) and checkInTime/checkOutTime. Every attempt to save failed. | frontend/src/pages/Attendance.jsx | Fixed | Aligned field names and enum casing with the shared Zod schema.
4 | Routine / Timetable | Critical | "Routine" page's Save button was a fake stub | Clicking Save Routine showed a success toast but never called any API — nothing was ever saved. A second, working page (Timetable) already implemented the same feature correctly. | frontend/src/pages/school/Routine.jsx (old) | Fixed | Removed the broken duplicate. The working Timetable implementation is now the single "Routine" page/route, per your instruction to rename Timetable to Routine (the term Nepali schools actually use).
5 | Ledger | Critical | Manual ledger entries were single-sided and unbalanced | The "New Entry" (Ledger) and "Add to Ledger" (Transactions) forms posted one row with no offsetting entry, and directly overwrote account balances instead of incrementing — breaking the fundamental debit=credit accounting rule and risking lost balance updates under concurrent edits. | backend/.../ledger-entry.service.impl.ts, frontend Ledger.jsx & Transactions.jsx | Fixed | Manual entries now require both a debit and a credit account and always post a balanced pair in one transaction, matching the pattern already used for every automated posting (sales, purchases, payroll, etc.). Deleting an entry now correctly reverses both legs' balances too (previously balance was never reversed on delete, even for the old single-sided design).
6 | Attendance (Staff) | High | Staff attendance update/delete ignored companyId | Any company could edit or delete another company's staff attendance record if they knew its ID — a cross-tenant data integrity/security gap. | backend/.../attendance.service.impl.ts | Fixed | update()/remove() now scope by companyId and throw 404 if the record doesn't belong to the caller's company.
7 | Attendance (Staff) | High | Staff attendance create() had no duplicate handling | Re-submitting attendance for the same employee+date (double-click, retry after an error) threw an unhandled Prisma unique-constraint error → 500, instead of updating the existing record. | backend/.../attendance.service.impl.ts | Fixed | create() now upserts on (employeeId, date).
8 | Attendance (Student) | High | SMS-on-absence had no idempotency guard | The student roster is resubmitted in full on every Save. Fixing one student's status re-sent the "your child is absent" SMS to every other already-absent student's guardian again — real cost and annoyance for parents. | backend/.../school.service.ts (saveAttendance) | Fixed | SMS now only fires for students whose status newly became ABSENT this save, compared against their prior status.
9 | Attendance (Student) | High | Dead useQuery onSuccess left local edits stale across date/class switches | onSuccess on useQuery was removed in TanStack Query v5 (this project's version), so switching class or date without saving could silently carry over another day's edits and overwrite the wrong date's attendance on next Save. | frontend/src/pages/school/StudentAttendance.jsx | Fixed | Replaced with a useEffect keyed on the fetched rows so local edits always re-sync to the currently viewed class/date.
10 | Attendance (Student) | Medium | Timezone-inconsistent date range in monthly attendance summary | getAttendanceSummary built month boundaries with a local-timezone Date constructor while every other attendance query used UTC-safe parsing — risked an off-by-one-day boundary shift if the server's timezone isn't UTC. | backend/.../school.service.ts (getAttendanceSummary) | Fixed | Boundaries now built with Date.UTC(...) to match the rest of the module.
11 | Roles / Security | High | Portal "set-password" endpoint had no role restriction | Any authenticated staff role — including TEACHER and LIBRARIAN — could reset a parent/student's portal login password. Only an office/admin action should be able to do this. | backend/.../portal.controller.ts | Fixed | Restricted to ADMIN and ACCOUNTANT. Recommend double-checking the frontend "Set Portal Password" button in Students.jsx is hidden for TEACHER/LIBRARIAN too, so they don't see a button that now 403s.
12 | Ledger | Medium | School Accounts Setup removed from Ledger | Per your instruction — the button, its API endpoint, and its backend service method have all been deleted cleanly (no orphaned references remain). | frontend Ledger.jsx, backend school.controller.ts / school-finance.service.ts, frontend api/index.ts | Fixed | Confirmed no other page referenced this feature.
13 | Invoicing | Medium | No QR code on fee receipts | The client wants "dynamic QR code" on invoices; nothing existed — no library, no logic, no template slot anywhere in the codebase. | frontend/src/lib/printFeeReceipt.js | Fixed (demo-only) | Added a QR code encoding receipt details (school, receipt no., student, amount, month) for quick visual verification. This is NOT a real bank/eSewa payment QR — do not present it to the client as a working payment QR. A real payment QR needs a chosen QR standard (Fonepay/NPR QR or eSewa merchant QR) and a merchant/gateway partnership — that's a separate, multi-day project.
14 | Banking | Medium | Banking not connected to school Fees | A full Bank Account module already existed in the general Transactions area, but recording a fee payment by bank never linked to a specific bank account or updated its balance. | backend school-finance.service.ts, prisma schema, frontend Fees.jsx | Fixed | Added FeePayment.bankAccountId (migration applied), a bank-account picker in the fee payment dialog, and the payment now updates that bank account's balance and creates a matching Transaction record.
15 | Payments | Low | eSewa/Khalti are on sandbox credentials | Working end-to-end today, but ESEWA_SECRET_KEY / KHALTI_SECRET_KEY in backend/.env are blank, so the app falls back to the gateways' public test keys. Fine for tomorrow's demo — must be swapped for real merchant credentials before accepting real money. | backend/.env | Unfixed (by design for demo) | Get real merchant credentials from eSewa/Khalti before going live and set them in backend/.env.
16 | Payments | Low | Parent portal only offers eSewa/Khalti, not Cash/Bank/Cheque | The admin counter Fees screen already supports Cash/Bank/Cheque/eSewa/Khalti. The self-service parent portal intentionally only shows the two online options, since a parent can't self-attest a cash payment. | frontend/src/pages/portal/PortalFees.jsx | Unfixed (appears intentional) | Confirm with the client this is the intended design — flagged only because it matched your description of "only eSewa and Khalti", but it looks like reasonable behavior for a self-service screen, not a bug.
17 | Calendar / BS-AD | Medium | Several school pages still show AD-only dates with no BS equivalent | Notices, Homework, Exam Schedule, Exam Results, Attendance date pickers, and several Portal pages use native AD-only date inputs with no Nepali date shown. The Events page has a BS entry but as a freeform "YYYY-MM-DD" text box, not a real calendar picker. | Multiple: Notices.jsx, Homework.jsx, ExamSchedule.jsx, Exams.jsx, StudentAttendance.jsx, Attendance.jsx, several Portal pages | Unfixed (logged) | The underlying conversion bug (root cause of "dates not converting") is fixed everywhere. Building one shared BS-aware date-picker component and rolling it out across ~10 pages is a multi-day UI project — recommend scheduling as a follow-up sprint, not attempting the night before a demo.
18 | Fees | Low | Fee "Month" field is freeform text, not a picker | Staff must type the BS month manually (e.g. "2081-Bhadra") with no validation — a source of typos/inconsistent formats across invoices. | frontend/src/pages/school/Fees.jsx (BillingRunDialog, NewInvoiceDialog, BulkInvoiceDialog) | Unfixed (logged) | Replace with a BS year/month dropdown once the shared date-picker component (above) is built.
19 | Ledger | Low | Fee-payment ledger posting bypasses the shared LedgerPostingService | school-finance.service.ts posts fee-payment ledger entries with its own raw Prisma logic instead of calling the LedgerPostingService already injected into the same class (which is never used). Today's amounts are correctly balanced, so there is no active bug — but any future change to account-naming/rounding conventions in LedgerPostingService will silently drift out of sync with this duplicate. | backend/.../school-finance.service.ts (postFeePayment) | Unfixed (logged — low risk) | Deliberately left alone tonight: it works correctly today, and refactoring working financial-posting code the night before a client demo is a needless risk. Recommend refactoring to call LedgerPostingService directly in a calmer week.
20 | i18n | Low | New finance/payroll/banking UI still missing Nepali translations | Fee payment dialog fields, payroll page, and the new bank-account picker fall back to English (no ne.json keys) — a pre-existing gap in the finance tabs that widened slightly with tonight's new fields. | frontend/src/locales/ne.json | Unfixed (logged) | Given the target audience (parents in rural areas), recommend a dedicated pass to add Nepali keys for every finance-related dialog before wider rollout.
21 | API layer | Medium | Generic legacy API adapter never sends companyId on update/delete | frontend/src/api/adapter.js's generic update()/delete() helpers don't pass companyId as a query param. Any backend endpoint that scopes update/delete by companyId via that query param (rather than deriving it from the auth token) will silently skip company-scoping when called through this adapter, because Prisma treats an undefined filter value as "no filter." Confirmed on the Ledger Account update path; likely affects other pages still using the legacy adapter. | frontend/src/api/adapter.js | Unfixed (logged) | Broader than one page — recommend a dedicated audit of every page still using the legacy api.* adapter for update/delete calls, not a one-night fix.
22 | Roles / Security | Low | Several endpoints rely on a class-level @Roles() default rather than an explicit per-method decorator | Not a bug — NestJS correctly falls back to the controller's class-level @Roles() when a method has none — but it does mean the role list is enforced twice-removed from the endpoint code, making it easy for a future developer to accidentally widen access by adding a method-level @Roles() that's less restrictive than intended. See the full endpoint-by-endpoint breakdown in the Role-Service Matrix tab. | Multiple controllers (see Role-Service Matrix) | Unfixed (informational) | No action needed now — flagged so whoever adds new endpoints later knows to check the class-level default before assuming "no @Roles() means locked down" (it does not — see next row).
23 | Roles / Security | Medium | RolesGuard defaults to ALLOW (not deny) when no @Roles() is present anywhere | If a future endpoint is added to one of the few controllers with no class-level @Roles() (e.g. PayrollController, EmployeeController) and the developer forgets to add @Roles(), ANY authenticated user — of any role — can call it. This is a fail-open design, confirmed in roles.guard.ts. | backend/src/modules/guards/roles.guard.ts | Unfixed (informational — architecture as designed) | Worth a team decision: consider flipping the default to fail-closed (deny unless @Roles() is present) for new controllers, since fail-open guards are a common source of accidental privilege escalation as a codebase grows.
24 | Routine/Timetable | Low | Dead unused icon imports left after Routine/Timetable consolidation | Clock and CalendarDays icon imports became unused in SidebarNav.jsx after merging the duplicate nav entries — cosmetic only, does not affect functionality. | frontend/src/components/layout/SidebarNav.jsx | Fixed | Cleaned up as part of the Routine/Timetable fix.
25 | Attendance | Info | No bulk staff-attendance marking UI (student side has "All Present"/"All Absent", staff side is one-at-a-time) | A BulkAttendanceSchema exists in the shared package but is wired to no controller — looks like a planned feature that was never finished. | frontend/src/pages/Attendance.jsx, shared/src/schemas/attendance.schema.ts | Unfixed (logged) | Not touched tonight — not reported as broken, just incomplete. Consider building a bulk-mark UI for staff attendance as a future enhancement.
26 | QR / Payments | Info | Demo QR is descriptive text only, not a scannable payment/verification link | No public "view receipt" page exists yet for the QR to link to, so it currently encodes plain text (school, receipt no., student, amount) rather than a URL. | frontend/src/lib/printFeeReceipt.js | Unfixed (logged) | If a real payment/verification QR is wanted later, build a public receipt-view route first, then point the QR at it.

## Role-Service Matrix
Role → Service Permission Matrix — School Management System
Roles: ADMIN, ACCOUNTANT, STAFF, TEACHER, LIBRARIAN. SUPER_ADMIN always has full access regardless of the table below. Parent/Student Portal uses a separate login system, listed at the bottom.
Note: rows marked "(class default)" have no @Roles() on that specific endpoint — NestJS falls back to the controller's class-level default shown. If NO @Roles() exists anywhere on a controller (see Payroll, Employee), ANY authenticated staff role can call it.
School — Dashboard | GET | /api/v1/school/dashboard | STAFF, ACCOUNTANT, ADMIN, TEACHER, LIBRARIAN | Shows the main school dashboard summary and analytics
School — Analytics | GET | /api/v1/school/analytics/attendance | STAFF, ACCOUNTANT, ADMIN, TEACHER | Student attendance analytics report
School — Analytics | GET | /api/v1/school/analytics/fees | STAFF, ACCOUNTANT, ADMIN | Fee collection analytics report
School — Analytics | GET | /api/v1/school/analytics/academics | STAFF, ACCOUNTANT, ADMIN, TEACHER | Academic performance analytics report
School — Analytics | GET | /api/v1/school/analytics/operations | STAFF, ACCOUNTANT, ADMIN | Operations analytics (hostel/transport/library)
Academic Years | GET | /api/v1/school/academic-years | STAFF, ACCOUNTANT, ADMIN, TEACHER | Lists the school's academic years
Academic Years | POST | /api/v1/school/academic-years | STAFF, ACCOUNTANT, ADMIN (class default) | Creates a new academic year
Academic Years | PUT | /api/v1/school/academic-years/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Updates an academic year
Academic Years | DELETE | /api/v1/school/academic-years/:id | ADMIN | Deletes an academic year
Classes | GET | /api/v1/school/classes | STAFF, ACCOUNTANT, ADMIN, TEACHER, LIBRARIAN | Lists all school classes/sections
Classes | POST | /api/v1/school/classes | STAFF, ACCOUNTANT, ADMIN (class default) | Creates a new class/section
Classes | PUT | /api/v1/school/classes/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Updates a class
Classes | DELETE | /api/v1/school/classes/:id | ADMIN | Deletes a class
Students | GET | /api/v1/school/students | STAFF, ACCOUNTANT, ADMIN, TEACHER, LIBRARIAN | Lists/searches students (paginated)
Students | GET | /api/v1/school/students/:id | STAFF, ACCOUNTANT, ADMIN, TEACHER, LIBRARIAN | Views a single student's profile
Students | POST | /api/v1/school/students | STAFF, ACCOUNTANT, ADMIN (class default) | Enrolls a new student
Students | PUT | /api/v1/school/students/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Updates a student profile
Students | DELETE | /api/v1/school/students/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Deletes a student record
Students | POST | /api/v1/school/students/promote | ADMIN | Promotes a batch of students to the next class
Students | POST | /api/v1/portal/set-password | ADMIN, ACCOUNTANT (fixed tonight — was open to any staff role) | Sets/resets a student's parent-portal login password
Subjects | GET | /api/v1/school/subjects | STAFF, ACCOUNTANT, ADMIN, TEACHER | Lists subjects, optionally by class
Subjects | POST | /api/v1/school/subjects | STAFF, ACCOUNTANT, ADMIN (class default) | Creates a new subject
Subjects | PUT | /api/v1/school/subjects/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Updates a subject
Subjects | DELETE | /api/v1/school/subjects/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Deletes a subject
Student Attendance | GET | /api/v1/school/attendance | STAFF, ACCOUNTANT, ADMIN, TEACHER | Views a class's attendance for one day
Student Attendance | POST | /api/v1/school/attendance | STAFF, ACCOUNTANT, ADMIN, TEACHER | Marks/saves student attendance for a class/day
Student Attendance | GET | /api/v1/school/attendance/report | STAFF, ACCOUNTANT, ADMIN, TEACHER | Class attendance report over a date range
Student Attendance | GET | /api/v1/school/attendance/summary | STAFF, ACCOUNTANT, ADMIN, TEACHER | One student's monthly attendance summary
Fees — Structures | GET | /api/v1/school/fee-structures | STAFF, ACCOUNTANT, ADMIN (class default) | Lists fee structures by class
Fees — Structures | POST | /api/v1/school/fee-structures | STAFF, ACCOUNTANT, ADMIN (class default) | Creates a fee structure
Fees — Structures | PUT | /api/v1/school/fee-structures/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Updates a fee structure
Fees — Structures | DELETE | /api/v1/school/fee-structures/:id | ADMIN | Deletes a fee structure
Fees — Invoices | GET | /api/v1/school/fee-invoices | STAFF, ACCOUNTANT, ADMIN (class default) | Lists/searches student fee invoices
Fees — Invoices | POST | /api/v1/school/fee-invoices | STAFF, ACCOUNTANT, ADMIN (class default) | Creates a single fee invoice
Fees — Invoices | POST | /api/v1/school/fee-invoices/bulk | ADMIN, ACCOUNTANT | Generates invoices in bulk for a class
Fees — Payments | PATCH | /api/v1/school/fee-invoices/:id/payment | STAFF, ACCOUNTANT, ADMIN (class default) | Records a fee payment (cash/bank/eSewa/Khalti — bank now requires a bank account)
Fees — Payments | GET | /api/v1/school/fee-invoices/:id/payments | STAFF, ACCOUNTANT, ADMIN (class default) | Lists payments made against an invoice
Fees — Heads | GET | /api/v1/school/fee-heads | STAFF, ACCOUNTANT, ADMIN (class default) | Lists fee heads/categories
Fees — Heads | POST | /api/v1/school/fee-heads | ADMIN, ACCOUNTANT | Creates a fee head
Fees — Heads | POST | /api/v1/school/fee-heads/defaults | ADMIN, ACCOUNTANT | Sets up standard default fee heads
Fees — Heads | PUT | /api/v1/school/fee-heads/:id | ADMIN, ACCOUNTANT | Updates a fee head
Fees — Heads | DELETE | /api/v1/school/fee-heads/:id | ADMIN | Deletes a fee head
Fees — Profile | GET | /api/v1/school/students/:id/fee-profile | STAFF, ACCOUNTANT, ADMIN (class default) | Views a student's full fee/billing profile
Fees — Scholarships | POST | /api/v1/school/students/:id/scholarships | ADMIN, ACCOUNTANT | Grants a scholarship/discount
Fees — Scholarships | DELETE | /api/v1/school/scholarships/:id | ADMIN, ACCOUNTANT | Removes a scholarship
Fees — Packages | GET | /api/v1/school/fee-packages | STAFF, ACCOUNTANT, ADMIN (class default) | Lists fee packages
Fees — Packages | POST | /api/v1/school/fee-packages | ADMIN, ACCOUNTANT | Creates a fee package
Fees — Packages | PUT | /api/v1/school/fee-packages/:id | ADMIN, ACCOUNTANT | Updates a fee package
Fees — Packages | DELETE | /api/v1/school/fee-packages/:id | ADMIN | Deletes a fee package
Fees — Packages | PATCH | /api/v1/school/students/:id/package | ADMIN, ACCOUNTANT | Assigns/unassigns a fee package to a student
Fees — Billing | POST | /api/v1/school/billing-run | ADMIN, ACCOUNTANT | Runs monthly fee billing across a class/company
Fees — Receipt | GET | /api/v1/school/fee-invoices/:id/receipt | STAFF, ACCOUNTANT, ADMIN (class default) | Generates a printable payment receipt (now with demo QR)
Exams | GET | /api/v1/school/exam-results | STAFF, ACCOUNTANT, ADMIN, TEACHER | Lists exam results
Exams | GET | /api/v1/school/exam-results/report-card | STAFF, ACCOUNTANT, ADMIN, TEACHER | Generates a student's report card
Exams | POST | /api/v1/school/exam-results | STAFF, ACCOUNTANT, ADMIN, TEACHER | Enters a new exam result
Exams | PUT | /api/v1/school/exam-results/:id | STAFF, ACCOUNTANT, ADMIN, TEACHER | Updates an exam result
Exams | DELETE | /api/v1/school/exam-results/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Deletes an exam result
Exam Schedule | GET | /api/v1/school/exam-schedules | STAFF, ACCOUNTANT, ADMIN, TEACHER, LIBRARIAN | Lists exam schedules
Exam Schedule | POST | /api/v1/school/exam-schedules | STAFF, ACCOUNTANT, ADMIN (class default) | Creates an exam schedule entry
Exam Schedule | PUT | /api/v1/school/exam-schedules/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Updates an exam schedule entry
Exam Schedule | DELETE | /api/v1/school/exam-schedules/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Deletes an exam schedule entry
Timetable / Routine | GET | /api/v1/school/timetable | STAFF, ACCOUNTANT, ADMIN, TEACHER | Views a class's weekly routine
Timetable / Routine | POST | /api/v1/school/timetable | STAFF, ACCOUNTANT, ADMIN (class default) | Creates/updates a routine slot
Timetable / Routine | DELETE | /api/v1/school/timetable/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Deletes a routine slot
Notices | GET | /api/v1/school/notices | STAFF, ACCOUNTANT, ADMIN, TEACHER, LIBRARIAN | Lists notices/announcements
Notices | POST | /api/v1/school/notices | STAFF, ACCOUNTANT, ADMIN (class default) | Creates a notice
Notices | PUT | /api/v1/school/notices/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Updates a notice
Notices | DELETE | /api/v1/school/notices/:id | ADMIN | Deletes a notice
Notices | POST | /api/v1/school/notices/:id/broadcast-sms | ADMIN | Sends a notice as an SMS blast to parents
SMS | POST | /api/v1/school/sms/fee-reminder/:invoiceId | STAFF, ACCOUNTANT, ADMIN (class default) | Sends an SMS fee-payment reminder
Events / Calendar | GET | /api/v1/school/events | STAFF, ACCOUNTANT, ADMIN, TEACHER, LIBRARIAN | Lists school calendar events
Events / Calendar | POST | /api/v1/school/events | STAFF, ACCOUNTANT, ADMIN (class default) | Creates a school event
Events / Calendar | PUT | /api/v1/school/events/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Updates a school event
Events / Calendar | DELETE | /api/v1/school/events/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Deletes a school event
Study Materials | GET | /api/v1/school/study-materials | STAFF, ACCOUNTANT, ADMIN, TEACHER | Lists study materials
Study Materials | POST | /api/v1/school/study-materials | STAFF, ACCOUNTANT, ADMIN, TEACHER | Uploads a study material
Study Materials | DELETE | /api/v1/school/study-materials/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Deletes a study material
Homework | GET | /api/v1/school/homework | STAFF, ACCOUNTANT, ADMIN, TEACHER | Lists homework assignments
Homework | POST | /api/v1/school/homework | STAFF, ACCOUNTANT, ADMIN, TEACHER | Assigns new homework
Homework | PUT | /api/v1/school/homework/:id | STAFF, ACCOUNTANT, ADMIN, TEACHER | Updates a homework assignment
Homework | DELETE | /api/v1/school/homework/:id | STAFF, ACCOUNTANT, ADMIN, TEACHER | Deletes a homework assignment
Library | GET | /api/v1/school/library/books | STAFF, ACCOUNTANT, ADMIN, LIBRARIAN | Lists the library book catalog
Library | POST | /api/v1/school/library/books | STAFF, ACCOUNTANT, ADMIN, LIBRARIAN | Adds a new book
Library | PUT | /api/v1/school/library/books/:id | STAFF, ACCOUNTANT, ADMIN, LIBRARIAN | Updates a book
Library | DELETE | /api/v1/school/library/books/:id | STAFF, ACCOUNTANT, ADMIN, LIBRARIAN | Removes a book
Library | GET | /api/v1/school/library/issues | STAFF, ACCOUNTANT, ADMIN, LIBRARIAN | Lists book issue/loan records
Library | POST | /api/v1/school/library/issues | STAFF, ACCOUNTANT, ADMIN, LIBRARIAN | Issues a book to a student
Library | PATCH | /api/v1/school/library/issues/:id/return | STAFF, ACCOUNTANT, ADMIN, LIBRARIAN | Records a book return (+ fine)
Hostel | GET | /api/v1/school/hostel/rooms | STAFF, ACCOUNTANT, ADMIN (class default) | Lists hostel rooms
Hostel | POST | /api/v1/school/hostel/rooms | STAFF, ACCOUNTANT, ADMIN (class default) | Creates a hostel room
Hostel | PUT | /api/v1/school/hostel/rooms/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Updates a hostel room
Hostel | DELETE | /api/v1/school/hostel/rooms/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Deletes a hostel room
Hostel | GET | /api/v1/school/hostel/allocations | STAFF, ACCOUNTANT, ADMIN (class default) | Lists hostel allocations
Hostel | POST | /api/v1/school/hostel/allocations | STAFF, ACCOUNTANT, ADMIN (class default) | Allocates a student to a room
Hostel | DELETE | /api/v1/school/hostel/allocations/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Removes a hostel allocation
Transport | GET | /api/v1/school/transport/routes | STAFF, ACCOUNTANT, ADMIN (class default) | Lists bus/transport routes
Transport | POST | /api/v1/school/transport/routes | STAFF, ACCOUNTANT, ADMIN (class default) | Creates a transport route
Transport | PUT | /api/v1/school/transport/routes/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Updates a transport route
Transport | DELETE | /api/v1/school/transport/routes/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Deletes a transport route
Transport | GET | /api/v1/school/transport/assignments | STAFF, ACCOUNTANT, ADMIN (class default) | Lists student transport assignments
Transport | POST | /api/v1/school/transport/assignments | STAFF, ACCOUNTANT, ADMIN (class default) | Assigns a student to a route
Transport | DELETE | /api/v1/school/transport/assignments/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Removes a transport assignment
Staff Attendance | GET | /api/v1/attendance | STAFF, ACCOUNTANT, ADMIN (class default) | Lists staff attendance records
Staff Attendance | GET | /api/v1/attendance/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Views one staff attendance record
Staff Attendance | POST | /api/v1/attendance | STAFF, ACCOUNTANT, ADMIN (class default) | Records staff attendance
Staff Attendance | PUT | /api/v1/attendance/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Updates a staff attendance record
Staff Attendance | DELETE | /api/v1/attendance/:id | STAFF, ACCOUNTANT, ADMIN (class default) | Deletes a staff attendance record
Payroll | GET | /api/v1/payroll/summary | ACCOUNTANT, ADMIN | Payroll summary for a month
Payroll | POST | /api/v1/payroll/process | ADMIN | Runs payroll for all active employees
Payroll | POST | /api/v1/payroll/calculate | ACCOUNTANT, ADMIN | Calculates payroll for one employee
Payroll | PATCH | /api/v1/payroll/:id/mark-paid | ADMIN | Marks a payroll record as paid
Payroll | PATCH | /api/v1/payroll/:id/hold | ADMIN | Puts payroll on hold / releases hold
Payroll | PATCH | /api/v1/payroll/:id/adjust | ACCOUNTANT, ADMIN | (New) Adjusts other deductions and recalculates net pay
Payroll | GET | /api/v1/payroll/gratuity | ACCOUNTANT, ADMIN | Calculates gratuity entitlement
Ledger — Accounts | GET | /api/v1/ledger/accounts | ACCOUNTANT, ADMIN (class default) | Lists ledger accounts
Ledger — Accounts | GET | /api/v1/ledger/accounts/:id | ACCOUNTANT, ADMIN (class default) | Views a ledger account
Ledger — Accounts | POST | /api/v1/ledger/accounts | ACCOUNTANT, ADMIN (class default) | Creates a ledger account
Ledger — Accounts | PUT | /api/v1/ledger/accounts/:id | ACCOUNTANT, ADMIN (class default) | Updates a ledger account
Ledger — Accounts | DELETE | /api/v1/ledger/accounts/:id | ACCOUNTANT, ADMIN (class default) | Deletes a ledger account
Ledger — Accounts | POST | /api/v1/ledger/accounts/:id/toggle-hidden | ADMIN | Hides/unhides an account (password re-entry required)
Ledger — Accounts | POST | /api/v1/ledger/accounts/hidden/search | ADMIN | Finds a hidden account by name (password required)
Ledger — Accounts | DELETE | /api/v1/ledger/accounts/:id/hidden | ADMIN | Permanently deletes a hidden account (password required)
Ledger — Entries | GET | /api/v1/ledger/entries | ACCOUNTANT, ADMIN (class default) | Lists ledger (journal) entries
Ledger — Entries | GET | /api/v1/ledger/entries/:id | ACCOUNTANT, ADMIN (class default) | Views a ledger entry
Ledger — Entries | POST | /api/v1/ledger/entries | ACCOUNTANT, ADMIN (class default) | (Fixed) Creates a balanced double-entry journal pair
Ledger — Entries | PUT | /api/v1/ledger/entries/:id | ACCOUNTANT, ADMIN (class default) | Edits an entry's description/date only (amounts are immutable)
Ledger — Entries | DELETE | /api/v1/ledger/entries/:id | ACCOUNTANT, ADMIN (class default) | (Fixed) Deletes both legs of a manual entry and reverses both balances
Banking | GET | /api/v1/bank-accounts | ACCOUNTANT, ADMIN (class default) | Lists bank accounts
Banking | GET | /api/v1/bank-accounts/:id | ACCOUNTANT, ADMIN (class default) | Views a bank account
Banking | POST | /api/v1/bank-accounts | ACCOUNTANT, ADMIN (class default) | Adds a bank account
Banking | PUT | /api/v1/bank-accounts/:id | ACCOUNTANT, ADMIN (class default) | Updates a bank account
Banking | DELETE | /api/v1/bank-accounts/:id | ACCOUNTANT, ADMIN (class default) | Deletes a bank account
Employees (HR) | GET | /api/v1/employees | ACCOUNTANT, ADMIN | Lists employees
Employees (HR) | GET | /api/v1/employees/:id | ACCOUNTANT, ADMIN | Views an employee
Employees (HR) | POST | /api/v1/employees | ACCOUNTANT, ADMIN | Creates an employee record
Employees (HR) | PUT | /api/v1/employees/:id | ACCOUNTANT, ADMIN | Updates an employee
Employees (HR) | DELETE | /api/v1/employees/:id | ADMIN | Soft-deletes (deactivates) an employee
Parent / Student Portal — separate login system (not the staff role table above)
Portal | POST | /api/v1/portal/login | Public | Parent/student logs into the portal with phone + password
Portal | GET | /api/v1/portal/me | Any logged-in parent/student (own child/account only) | Fetches the logged-in student's profile
Portal | GET | /api/v1/portal/attendance | Any logged-in parent/student (own child/account only) | Shows the student's own attendance history
Portal | GET | /api/v1/portal/fees | Any logged-in parent/student (own child/account only) | Shows the student's own fee invoices/balances
Portal | GET | /api/v1/portal/fees/:invoiceId/receipt | Any logged-in parent/student (own child/account only) | Downloads a receipt for the student's own payment
Portal | GET | /api/v1/portal/results | Any logged-in parent/student (own child/account only) | Shows the student's own exam results
Portal | GET | /api/v1/portal/homework | Any logged-in parent/student (own child/account only) | Shows homework for the student's class
Portal | GET | /api/v1/portal/notices | Any logged-in parent/student (own child/account only) | Shows school notices/announcements
Portal | GET | /api/v1/portal/timetable | Any logged-in parent/student (own child/account only) | Shows the student's class routine
Portal | POST | /api/v1/portal/pay/esewa/:invoiceId | Portal login required — PARENT only | Starts an eSewa payment for a fee invoice
Portal | POST | /api/v1/portal/pay/esewa/verify | Public (eSewa redirect callback) | Confirms an eSewa payment after redirect back
Portal | POST | /api/v1/portal/pay/khalti/:invoiceId | Portal login required — PARENT only | Starts a Khalti payment for a fee invoice
Portal | POST | /api/v1/portal/pay/khalti/verify | Public (Khalti redirect callback) | Confirms a Khalti payment after redirect back